Recluse Community Trust Minutes

December 15, 2010

Members Present:  Cate and Amber Loetscher, Mike Manor, Marilyn Mackey, Marge Means, Jo Rogers and Kathy Spellman.

Community members present: Bruce and Wes from S & S Building.

The meeting was called to order by Chairman Marilyn Mackey.

Marilyn appointed Amber as acting secretary.

Agenda:  Cate moved to approve the agenda as presented, Jo seconded the motion and it passed.

Secretary’s Report:  No report was given.

Treasurer’s Report: No report was given.

New Business:

Kitchen:

Countertops:  We discussed the color of the counters as being the dark color chosen by the Trust earlier.  Wes and Bruce suggested ordering a extra sheet of laminate to use for the bathroom counters.  We did agree by consensus.

Sinks and Faucet:  We discussed ordering the sink faucets from one of the catalogs.  We discussed using an long goose neck with a squirt nozzle.  We tabled this subject.

S & S’s Request for Extension:

Wes and Bruce requested that the Trust grant the full 18 day extension.  They explained the pivotal nature of the concrete floor being poured first.  The lack of the floor does not allow for several projects to be completed concurrently.  They also pointed out that the decision to call a weather day is made early each morning.  We discussed revisiting this extension until early January went we will have a better idea of the weather days.

Septic System:

The existing design calls for a 2000 gal septic tank.  We have located two 1000 gal tanks that together are about $1,000 cheaper.  If the DEQ does not have any concerns we will move forward with the installation within two weeks.  We will need some help installing them.  This well be after Christmas.  The county will be inspecting.

Propane:

S & S wanted to know which company the Trust wanted to use.  Marilyn suggested the Farmers Coop. as the fill company.

Power meter:

Kathy talked with PREC. About running the arena and building off of one meter.  This can not be done.  We discussed shutting the arena meter off.  No action was taken.

The next progress meeting is on Dec 27th at 10 a.m.

The meeting was adjourned.

Respectfully submitted,

Amber Loetscher

Acting Secretary

Approved on ________________of _________________2010

Marilyn Mackey, Recluse Community Trust President

Nancy Sorenson, Recluse Community Trust Secretary